SUBOP Software United Business Operation Platform Feasibility Report — First Draft

| Project | SUBOP — Software United Business Operation Platform |
| --- | --- |
| Document | Feasibility Report — First Draft |
| Version | v1 · Week 6 · 15 June 2026 |
| Owner | Abdalla |
| Status | First Draft — Sections 1 and 2 complete; Section 3 to be finalised in Week 7 |
| Final Version Due | Week 7 — 28 June 2026 (pending M2W6T9 abstraction layer recommendation from Omer) |

Draft Note: Section 3 (Market Feasibility) is intentionally brief and will be expanded in Week 7 once competitor analysis conclusions are finalised. Technical feasibility ratings will be reviewed after M2W6T9 abstraction layer recommendation is committed.

1.  Technical Feasibility

Each of the nine SUBOP platform modules is assessed against three ratings: Confirmed Feasible (technology proven, team capable, no significant unknowns); Feasible with Risk (achievable but carrying design complexity, skill gap, or timeline risk requiring active mitigation); Uncertain (significant unknowns that may require scope adjustment). Module codes reference Goal definitions in the Final Goal Statement document.

| G1 — Database-Agnostic Abstraction Layer | Feasible with Risk | M4 |
| --- | --- | --- |
| Assessment: The Adapter Pattern combined with SQLAlchemy Core is the confirmed implementation approach per M2W6T9 abstraction layer research. SQLAlchemy Core handles dialect differences for PostgreSQL, MySQL, and MSSQL automatically; cx_Oracle covers Oracle. The technical approach is well-documented and the required technology stack is mature. |  |  |
| Risk: This is the architecturally most critical module in the project. An under-designed abstraction interface propagates technical debt into every downstream module — ETL Engine, CDC, DW, Quality, and Lineage. Omer has no prior experience designing abstraction layers. The M3 architecture document must specify the BaseConnector interface precisely — including error handling contract and dialect override points — before M4 coding begins. |  |  |

| G2 — Connector Framework | Confirmed Feasible | M4 / M6 |
| --- | --- | --- |
| Assessment: Omer has built and pytest-validated working PostgreSQL and MySQL connectors with 10 passing tests as of M2 Week 6. The connector interface — ConnectionConfig, connect(), execute_query(), execute_write(), health_check(), ConnectorError — is tested and stable. Each additional connector follows the same pattern; implementation effort scales linearly. |  |  |
| Risk: Connector complexity escalates for Oracle (cx_Oracle driver management and licensing overhead) and Cassandra (CQL query model differs from SQL). Simpler connectors — PostgreSQL, MySQL, REST API, CSV — must be built and validated first in M4 before high-complexity sources are attempted in M6. |  |  |

| G3 — ETL Engine | Confirmed Feasible | M5 |
| --- | --- | --- |
| Assessment: Python ETL at the 1 million rows per 5 minutes scale is achievable with vectorized pandas operations and a properly designed batch processing loop. The stack — psycopg2/SQLAlchemy Core for extraction, pandas for transformation, SQLAlchemy Core for loading — is mature and proven at this scale. Batch, incremental, and parallel execution modes are all implementable within the M5 window. |  |  |
| Risk: Parallel processing requires careful concurrency design to avoid connection pool exhaustion across concurrent pipeline runs. Error recovery strategy — what happens when a batch fails mid-run and how partial state is preserved — must be specified in the M5 task plan before implementation begins. |  |  |

| G4 — CDC & Real-Time Streaming | Feasible with Risk | M7 |
| --- | --- | --- |
| Assessment: Debezium + Apache Kafka is the industry-standard open-source CDC stack. PostgreSQL WAL-level change capture via Debezium is well-documented; MySQL binlog CDC is also confirmed supported. The sub-30 second end-to-end latency KPI is achievable with this architecture. The Docker Compose dev environment already includes Kafka and ZooKeeper containers from M1 infrastructure setup. |  |  |
| Risk: HIGH: this module carries the highest learning-curve risk in the project. Omer has no prior experience with Kafka, ZooKeeper, or Debezium. The M7 development window (5 weeks, October to November 2026) is tight for a first distributed streaming implementation. Kafka self-study must begin no later than M5 Week 14 (August 2026). Oracle CDC via LogMiner is formally classified as Uncertain and scoped as a stretch goal: LogMiner setup complexity, supplemental logging requirements, and the team experience gap make a production-grade Oracle CDC implementation within the project timeline unrealistic. |  |  |

| G5 — Metadata-Driven Data Warehouse | Feasible with Risk | M8 |
| --- | --- | --- |
| Assessment: Auto-generating CREATE TABLE statements, SCD Type 2 merge logic, and schema versioning from a metadata specification is implementable using SQLAlchemy DDL expression language. The 80% faster than manual schema creation KPI is achievable because automation eliminates repetitive manual SQL writing for standard star and snowflake patterns. |  |  |
| Risk: The metadata DSL — the specification format that drives schema auto-generation — must be carefully designed during M3 before M8 begins. If too rigid it fails for non-standard schemas; if too flexible, the generation logic becomes unimplementable in M8. The metadata schema design is the second most important M3 architecture decision after the connector interface, and must be resolved before M4 so that earlier modules emit compatible metadata from the start. |  |  |

| G6 — BI Dashboard & OLAP Layer | Confirmed Feasible | M9 |
| --- | --- | --- |
| Assessment: Beyza completed the full SUBOP design system, component pattern library, UI shell architecture plan, and responsive layout specification in M2. Shell builds are planned across M5 through M8, meaning M9 is data wiring and final integration rather than from-scratch development. The data access path — Dashboard to FastAPI REST API to PostgreSQL warehouse query to JSON response — is a standard, well-documented architecture with no significant implementation unknowns. |  |  |
| Risk: The 15-minute dashboard creation KPI is the most UX-dependent metric in the project. Its achievement depends on the quality of the drag-and-drop builder UX, not just functional correctness. Beyza must include timed user testing in M9 against this benchmark before the M12 pilot begins. |  |  |

| G7 — Data Quality & Profiling | Confirmed Feasible | M10 |
| --- | --- | --- |
| Assessment: The five quality rule types — null checks, duplicate detection, format validation, range boundary checking, and ML-based anomaly detection — are implementable as a class-based rule engine in Python. Quality scoring as a weighted pass rate per dataset is straightforward aggregation. The anomaly detection prototype uses scikit-learn IsolationForest, a well-documented algorithm. |  |  |
| Risk: The rule engine must be architected for extensibility. A hard-coded implementation per rule type will become brittle as new rule types are added. M10 must use a registry-based or plugin-based rule engine design pattern. This is a moderate architectural design risk, not a technical feasibility uncertainty. |  |  |

| G8 — Data Lineage & Catalog | Feasible with Risk | M10 |
| --- | --- | --- |
| Assessment: Lineage tracking as a directed graph stored in PostgreSQL (adjacency list: source_node, target_node, edge_type, pipeline_id) is a proven pattern. Graph traversal uses NetworkX in Python. The catalog — searchable inventory of data assets — is implementable as a PostgreSQL table with full-text search indexes and a FastAPI query endpoint. |  |  |
| Risk: Full source-to-dashboard lineage traceability has a critical upstream dependency: every module from M4 onwards must emit consistent lineage metadata at each processing stage — connector to ETL job to warehouse table to BI field. If earlier modules are built without lineage instrumentation, M10 cannot reconstruct the graph retroactively. The lineage metadata schema must be defined in the M3 architecture document before M4 development begins. |  |  |

| G9 — Security & Compliance | Feasible with Risk | M11 |
| --- | --- | --- |
| Assessment: JWT-based authentication, FastAPI dependency injection for RBAC, and SQLAlchemy-level column masking are mature, well-documented patterns. The KVKK/GDPR compliance API surface — ten checklist items C01 through C10 from the M2W6T2 compliance research — is formally specified with endpoint definitions, module assignments, and implementation notes. |  |  |
| Risk: The compliance surface is broad: 10 checklist items spanning four modules — Connector Framework, ETL Engine, Metadata-Driven DW, and Security. Any item missed in M11 creates regulatory risk for pilot organisations. M11 implementation must treat the C01 through C10 checklist as a formal acceptance criterion. Audit logging performance overhead must be validated under load testing in M11 to confirm the 99.5% uptime KPI is unaffected. |  |  |

Technical Feasibility Summary

| Module | Rating | MS | Primary Risk Note |
| --- | --- | --- | --- |
| G1 — Database-Agnostic Abstraction Layer | Feasible with Risk | M4 | This is the architecturally most critical module in the project. |
| G2 — Connector Framework | Confirmed Feasible | M4 / M6 | Connector complexity escalates for Oracle (cx_Oracle driver management and licensing overhead) and Cassandra (CQL query model differs from SQL). |
| G3 — ETL Engine | Confirmed Feasible | M5 | Parallel processing requires careful concurrency design to avoid connection pool exhaustion across concurrent pipeline runs. |
| G4 — CDC & Real-Time Streaming | Feasible with Risk | M7 | HIGH: this module carries the highest learning-curve risk in the project. |
| G5 — Metadata-Driven Data Warehouse | Feasible with Risk | M8 | The metadata DSL — the specification format that drives schema auto-generation — must be carefully designed during M3 before M8 begins. |
| G6 — BI Dashboard & OLAP Layer | Confirmed Feasible | M9 | The 15-minute dashboard creation KPI is the most UX-dependent metric in the project. |
| G7 — Data Quality & Profiling | Confirmed Feasible | M10 | The rule engine must be architected for extensibility. |
| G8 — Data Lineage & Catalog | Feasible with Risk | M10 | Full source-to-dashboard lineage traceability has a critical upstream dependency: every module from M4 onwards must emit consistent lineage metadata at each processing stage — connector to ETL job to warehouse table to BI field. |
| G9 — Security & Compliance | Feasible with Risk | M11 | The compliance surface is broad: 10 checklist items spanning four modules — Connector Framework, ETL Engine, Metadata-Driven DW, and Security. |

2.  Resource Feasibility

The SUBOP team comprises three members with differentiated responsibilities. Abdalla leads project management, ETL architecture, data quality, and documentation (40%). Beyza owns BI, UI/UX, and frontend delivery (40%). Omer handles backend connectors, infrastructure, and security implementation with workload intentionally capped at 20% to reflect first-year student constraints. This section documents current skill gaps per high-risk module, the milestone window in which each gap must be closed, and the structured study plan for Omer on the two highest-risk skill areas — Kafka/Debezium and abstraction layer design. References to formally documented risks draw from risk_assumptions_final_v1.docx produced in Milestone 1.

2.1  Skill Gap Analysis

| Module | Skill Gap | Level | Study Window | Owner |
| --- | --- | --- | --- | --- |
| G1 — DB Abstraction | Adapter Pattern design; SQLAlchemy Core dialect system; abstraction layer architecture | High | M3 — July 2026 | Omer |
| G4 — CDC / Kafka | Apache Kafka architecture, ZooKeeper coordination, Debezium deployment and configuration | High | M5–M6 — Aug–Sep 2026 | Omer |
| G4 — Oracle CDC | Oracle LogMiner, supplemental logging, cx_Oracle advanced configuration | Uncertain | N/A — stretch goal only | Omer |
| G6 — BI Dashboard | Production React component development; state management; drag-and-drop builder UX | Medium | M5–M8 shell builds | Beyza |
| G8 — Lineage / Catalog | Graph data structures; NetworkX; PostgreSQL full-text search implementation | Low–Medium | M10 — Dec 2026–Jan 2027 | Abdalla + Omer |
| G9 — Security / KVKK | FastAPI RBAC dependency injection; JWT; KVKK/GDPR C01–C10 compliance API design | Medium | M10 — Nov–Dec 2026 | Omer + Abdalla |

2.2  Structured Self-Study Plan — Kafka / Debezium (Omer)

The CDC module (G4, M7) carries the highest learning-curve risk in the project. Study is not additional overhead — it replaces lower-priority connector tasks in M5–M6 if time pressure mounts.

| MS | Window | Owner | Required Action and Expected Output |
| --- | --- | --- | --- |
| M3 | Jul 2026 | Omer | Study Adapter Pattern (Martin Fowler — Patterns of Enterprise Application Architecture, Adapter chapter). Read SQLAlchemy Core dialect documentation in full. Implement abstraction layer prototype as part of the M3 architecture document. Output: BaseConnector interface committed to GitHub before M4 begins. |
| M5 | Aug 2026 | Omer | Begin Kafka structured self-study. Resources: Confluent Kafka documentation (free online); Kafka — The Definitive Guide (O'Reilly, free PDF via Confluent). Targets: producer/consumer model, topic partitioning, offset management, Kafka Connect architecture. Complete Chapters 1 through 5 before M6 begins. |
| M6 | Sep 2026 | Omer | Continue Kafka study alongside M6 connector expansion work. Study Debezium configuration specifically for PostgreSQL (WAL replication slot) and MySQL (binlog). Build and commit a Debezium plus Kafka plus PostgreSQL CDC proof-of-concept to GitHub. This PoC is the prerequisite gate for M7 starting on schedule. |
| M7 | Oct–Nov 2026 | Omer | Implement the full CDC module using Kafka and Debezium knowledge accumulated in M5 and M6. Abdalla provides architectural guidance on event schema normalisation and the ETL-to-CDC pipeline handoff. Kafka must be operational knowledge at M7 start — no additional study time is available in the M7 window. |

3.  Market Feasibility — Pilot Organisation Profiles

Brief Draft — Week 6: Three pilot organisation profiles are outlined below. Full market feasibility analysis — incorporating competitor analysis conclusions from M2W7T1 and market sizing data — will be added in Week 7.

| PP1 | University IT Department |  |
| --- | --- | --- |
| Profile |  | Mid-size Turkish public or private university — 15,000 to 30,000 students. |
| Infrastructure |  | PostgreSQL-based Student Information System (SIS); Excel-based HR and payroll data; isolated departmental databases (library, careers, accommodation systems). |
| SUBOP Use Case |  | Unified ETL consolidating SIS, HR, academic performance, and financial aid data into a central warehouse. BI dashboards for enrollment trends, academic performance by faculty, HR reporting, and budget monitoring. |
| Compliance |  | Strong KVKK obligation: universities process student personal data including TC ID numbers, academic records, and health data for disability accommodations. Special category data handling required. VERBiS registration likely mandatory. |
| Fit Assessment |  | Strong. PostgreSQL source aligns with Phase 1 connector targets already tested in M2. No enterprise BI licensing budget available — SUBOP open-source model directly addresses the cost constraint. KVKK compliance module directly addresses the regulatory obligation. |
| Contact Timeline |  | Identify a specific university IT director or data engineering contact by January 2027 (M11 phase). |

| PP2 | Regional Logistics / Supply Chain Company |  |
| --- | --- | --- |
| Profile |  | SME logistics or supply chain company — 200 to 500 employees, operations across Turkey and EU trade corridors. |
| Infrastructure |  | MSSQL-based ERP for operations and fleet management; MySQL-based CRM for customer accounts; Excel-based financial consolidation; no unified data layer. |
| SUBOP Use Case |  | CDC pipelines from MSSQL ERP and MySQL CRM providing near-real-time operational dashboards: delivery KPI tracking, route performance, customer order status, fleet utilisation. Batch ETL for financial consolidation and management reporting. |
| Compliance |  | Dual obligation: KVKK for Turkish customer and employee data; GDPR for EU customer shipping and contact data. Cross-border data transfer provisions under both regulations are relevant to pipeline design. |
| Fit Assessment |  | Strong CDC validation target — MSSQL and MySQL multi-source CDC tests the G4 module against two database engines simultaneously. Validates the sub-30 second latency KPI in a near-real-time operational context. |
| Contact Timeline |  | Identify via Ankara or Istanbul logistics sector industry contacts or university advisor network by January 2027. |

| PP3 | Healthcare or Finance Organisation |  |
| --- | --- | --- |
| Profile |  | Regional private hospital, healthcare group, or insurance company — 100 to 500 employees. |
| Infrastructure |  | Oracle-based Hospital Information System or insurance core system where Oracle is in use; PostgreSQL or MSSQL-based systems as the preferred lower-risk alternative. Siloed departmental reporting in Excel. |
| SUBOP Use Case |  | ETL from HIS or core system into a compliant warehouse. BI dashboards for clinical performance, patient flow, insurance claims, or underwriting analytics. Data quality monitoring on patient or claims records. RBAC enforcing role-level access control to sensitive health or financial data. |
| Compliance |  | Highest KVKK obligation: health and financial data are special category personal data requiring explicit consent, column-level masking per role, and a complete audit trail for every data access event. |
| Fit Assessment |  | Strongest validation target for G9 Security and Compliance and the C01 through C10 KVKK/GDPR checklist. Oracle-based HIS depends on Oracle CDC feasibility (currently Uncertain) — a PostgreSQL-based hospital system is the preferred alternative. Finance organisations on MSSQL are a lower-risk substitute. |
| Contact Timeline |  | Regulatory sensitivity requires early engagement. Begin outreach by November 2026 (M7 phase) to allow time for data sharing agreement negotiation. |