SUBOP

Milestone 6 Completion Checklist

This checklist walks through every success criterion defined in the Milestone 6 charter (Connector Ecosystem Expansion), verified against the live repository on the develop branch and against this week’s evidence: the merged develop-to-main CI run and local spot-checks. Each item is marked Done or Pending with a named resolution path. As of Week 21 (Friday 2 October 2026), eight of ten criteria are confirmed Done; two are Pending, each with a documented resolution plan and owner: the production CORS origin (Criterion 7) and the Week 21 advisor report (Criterion 9).

Audit notes. (1) A fresh diff of the main and develop branches after PR #28 found them byte-identical. (2) CI details for PR #28 (workflow run #253) come from the T4 verification note and the run link; they were not independently re-opened because the GitHub API was rate-limited during the audit. (3) Beyza’s component_status_m6_handoff_v1.md is at services/bi-dashboard/frontend/planning/, not docs/frontend/planning/ as the plan assumes. This does not block any criterion.

Section 1 — Success Criteria

| # | M6 Success Criterion | Status | Evidence / Resolution Plan |
| --- | --- | --- | --- |
| 1 | Lineage column_types wiring gap fixed: executor.py supplies column_types to execute_query(), and a rerun of the end-to-end demo shows non-zero lineage entries where it previously showed zero. | Done | - executor.py now derives column_types from the pipeline's type_cast steps (_column_types_from_casts) and passes them into the source read (M6W18T2); Week 19 added the SQLite type mapping so SQLite-sourced pipelines produce lineage too (M6W19T3). - Rerun after the fix showed non-zero lineage entries (previously 0), confirmed by Abdullah in Week 18. The exact entry count was not recorded. |
| 2 | DSL's mongodb connector_type removed from pipeline.py's validated set, with a test confirming rejection. | Done | - pipeline.py's _VALID_CONNECTOR_TYPES contains exactly the eight real connectors; mongodb is absent. - tests/test_pipeline.py::test_mongodb_connector_type_rejected covers the rejection, and /api/kpis tests also assert mongodb is not in the registry. |
| 3 | Eight working connectors (PostgreSQL, MySQL, MSSQL, SQLite, CSV, JSON, REST API, Oracle), each implementing the shared interface and raising the ConnectorError hierarchy. | Done | - All eight modules exist in services/connectors/ and are registered, validated and conformance-tested; see the 8 × 5 matrix in Section 2. - Spot-checked on a local machine: test_get_kpis_reports_all_eight_connectors passed, /api/kpis returned connector_count 8, and the dashboard's Connectors card displayed 8. |
| 4 | Connector test framework: one shared conformance suite run against every connector, passing for all eight. | Done | - tests/test_connector_conformance.py parametrizes one suite across all eight connector types (CONNECTOR_TYPES, M6W20T3). It has no skip: an unreachable database fails the test. - Passed in CI against live PostgreSQL, MySQL, MSSQL and Oracle containers (run 36826413529). |
| 5 | PipelineCreationForm mounted into PipelinesPage behind a visible action, and a pipeline created through the UI reaches succeeded end to end. | Done | - PipelinesPage.tsx imports and renders PipelineCreationForm (verified in source); the connector list offers all eight connectors. - A pipeline created through the UI by Beyza reached succeeded status, reported by Abdullah (Week 20). The run ID was not recorded. |
| 6 | Connection-ref env vars (SUBOP_CONN_PG_MAIN, SUBOP_CONN_DW_MAIN) present and resolvable via the SUBOP_CONN_{UPPERCASED_SLUG} convention. | Done | - Both are defined for the subop-api container in docker-compose.yml. - .env.example now uses the JSON format connection_resolver.py actually parses, and adds Oracle, file-kind and url-kind examples (M6W21T1). All values were parsed with json.loads and checked against the resolver's required fields. |
| 7 | Responsive design pass complete across the frontend's primary breakpoints, and CORS allow_origins updated for the production URL. | Pending | - Responsive half Done: DataTable's card-stack layout and the 767px boundary landed in M6W21T11. - CORS half Pending: no production URL exists yet. allow_origins is read from SUBOP_CORS_ORIGINS, which currently lists only localhost:5173 and localhost:5174. - Resolution plan: add the production URL to SUBOP_CORS_ORIGINS (in .env.example and the deployment environment) as soon as a deployment target exists. Proposed owner: Omer (roadmap role: infrastructure), to be confirmed at the M7 kickoff. |
| 8 | Full regression suite, including the connector test framework, passes in a clean-environment CI run, with Black and flake8 passing against max-line-length = 100. | Done | - PR #28 (develop into main), workflow run #253: both "Lint (Black + flake8)" and "Tests (pytest)" succeeded. https://github.com/Jeylani-2526/subop/actions/runs/36826413529 - Black and flake8 also re-run clean locally against services/ (Black: 23 files unchanged; flake8: no output). |
| 9 | Weekly advisor progress reports for Weeks 18, 19, 20 and 21 sent on schedule. | Pending | - Week 21 report is outstanding: due Sunday 4 October EOD (M6W21T7). - Reports are emailed to Emrah, not committed, so sending of Weeks 18 to 20 cannot be verified from the repository. Abdullah to confirm. |
| 10 | M6 Completion Checklist confirms every success criterion is marked Done or has a documented resolution plan before Milestone 7 begins. | Done | - This document. Both Pending items (7 and 9) carry a resolution plan and owner, listed in Section 3. |

Section 2 — 8+ Connector KPI Validation Matrix

Each of the eight connectors was checked at five checkpoints directly in the code on develop; checkpoint 5 is the clean-environment CI run: run 36826413529 (PR #28, workflow run #253), which ran the conformance suite against live PostgreSQL, MySQL, MSSQL and Oracle containers with no skip.

| Connector | 1. Module exists | 2. In _CONNECTOR_CLASSES | 3. In _VALID_CONNECTOR_TYPES | 4. In conformance CONNECTOR_TYPES | 5. Green clean-env CI run |
| --- | --- | --- | --- | --- | --- |
| PostgreSQL postgres_connector.py | Yes | Yes | Yes | Yes | Yes |
| MySQL mysql_connector.py | Yes | Yes | Yes | Yes | Yes |
| MSSQL mssql_connector.py | Yes | Yes * | Yes | Yes | Yes |
| SQLite sqlite_connector.py | Yes | Yes | Yes | Yes | Yes |
| CSV csv_connector.py | Yes | Yes | Yes | Yes | Yes |
| JSON json_connector.py | Yes | Yes | Yes | Yes | Yes |
| REST API rest_api_connector.py | Yes | Yes | Yes | Yes | Yes |
| Oracle oracle_connector.py | Yes | Yes | Yes | Yes | Yes |

* MSSQL registers only when the ODBC driver is available. It was installed in CI and on the local test machine.

Result: the roadmap’s 8+ working connectors KPI is met inside Milestone 6, ahead of its end-of-October 2026 validation date. Local spot-check: test_get_kpis_reports_all_eight_connectors passed, /api/kpis returned connector_count 8, and the dashboard’s Connectors card displayed 8.

Section 3 — Items Carried into Milestone 7

| Item | Resolution plan | Owner | Target |
| --- | --- | --- | --- |
| CORS allow_origins for the production URL (Criterion 7) | Add the production URL to SUBOP_CORS_ORIGINS once a deployment target exists. Owner proposed: Omer; confirm at M7 kickoff. | Omer (proposed) | When deployment exists |
| Week 21 advisor report (Criterion 9) | Send the M6-closing report to Emrah. | Abdullah | Sun 4 Oct 2026 EOD |
| Omer capacity question | Decided explicitly as the first item of the M7 kickoff (Part A, item 1) and recorded in Part B, not carried again. | Abdullah (facilitates) | M7 kickoff |
| Data Quality rule engine | Still a stub: /api/kpis reports average_quality_score as null. Full implementation is planned M10 scope. | Team | M10 |

SUBOP Project · Milestone 6 · Connector Ecosystem Expansion